## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME:
INTERN NAME:
DOCUMENT NAME: | TEST PLAN
CREATED ON: | 20/01/2024
Purpose of Document
A Test Plan is a detailed document that describes the test strategy, objectives, schedule, estimation, deliverables, and resources required to perform testing for a software product.
Test Plan helps us determine the effort needed to validate the quality of the application under test.
The test plan serves as a blueprint to conduct software testing activities as a defined process, which is minutely monitored and controlled by the test manager
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments are added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled

## TEST PLAN
TEST PLAN
PROJECT NAME | JobStart Fullstack Mern Application
PROJECT ID
INTERN NAME | Austin Doraiswamy
PROJECT MANAGER | Harshada Topale
INTRODUCTION
(Brief introduction of the test strategies, process, workflow and methodologies used for the project)
for "Job Start" fullstack MERN app, we follow Agile methodology, breaking tasks into sprints. Testing includes unit tests for backend logic, React component, and end-to-end tests. Continuous integration ensures code quality. Cloudinary integration tested for file uploads. JWT authentication verified extensively. our apps uses Mongodb atlas as non relational database.
SCOPE
IN SCOPE (Defines the features, functional or non-functional requirements of the software that will be tested)
Functional Requirements: User Authentication: Users should be able to register, log in, and log out securely using JWT authentication. Job Listings: Users can browse and search for job listings based on various criteria such as location, industry, job title, etc. Job Application: Users should be able to apply for jobs by submitting their resumes and cover letters through the platform. Profile Management: Users can create and manage their profiles, including updating personal information, uploading a resume, and viewing application history. Admin Panel: Administrators should have the ability to manage job listings, user accounts, and review/approve job applications. Non-functional Requirements: Security: Ensure data privacy and integrity through secure storage of sensitive information like user credentials and application documents. Performance: The application should handle a large number of concurrent users and job listings efficiently without significant performance degradation. Scalability: The system should be designed to easily scale horizontally to accommodate increasing user and job listing loads. Usability: The user interface should be intuitive and easy to navigate, providing a seamless experience for both job seekers and recruiters. Reliability: The application should be highly available and resilient, with minimal downtime or service interruptions.
OUT SCOPE (Defines the features, functional or non-functional requirements of the software that will NOT be tested)
Job Placement Services: The application will not provide job placement services or guarantee employment opportunities. Legal Compliance: While the application may provide basic guidelines, it will not offer legal counsel or ensure legal compliance for job postings, contracts, or any other legal aspects related to employment. External Training or Certification: The platform will not offer training programs or certification courses directly. Employment Verification: The application will not undertake employment verification services for users or employers. Financial Transactions: The platform will not handle financial transactions related to job placements.
QUALITY OBJECTIVE
(Mention the overall objective that you plan to achieve without your testing)
Functional Requirement Objectives: Validate that all features and functionalities specified in the requirements documentation are implemented correctly and perform as expected. Non-Functional Requirement Validation: Ensure that the application meets specified non-functional requirements such as performance, scalability, security, and usability. Quality Specification Adherence: Confirm that the application aligns with the quality standards defined by the client or industry best practices. Bug Identification and Resolution: Detect and rectify any bugs or issues present in the application before it goes live.
ROLES AND RESPONSIBILITIES
(Detail description of the Roles and responsibilities of different team members)
QA Analyst: Responsible for ensuring the quality of software products by designing test plans, executing tests, and identifying defects. Test Manager: Oversees the testing process, coordinates testing efforts, and manages resources to ensure the timely and effective execution of testing activities. Configuration Manager: Manages software configurations, including version control, release management, and configuration item identification. Developers: Design, develop, and maintain software applications according to project requirements and coding standards. Installation Team: Installs and configures software products in various environments, ensuring smooth deployment and functionality.
TEST METHODOLOGY
OVERVIEW (Mention the reason of adopting a particular test methodology for the project)
Agile: Emphasizes flexibility, collaboration, and customer feedback. Testing is integrated throughout development sprints.
TEST LEVELS (Define the Types of Testing to be executed on the Application Under Test (AUT))
The "Job Start" MERN application, suggested testing levels include unit testing for individual components, integration testing for combined modules, and system testing for end-to-end functionality verification, considering project scope and time
BUG TRIAGE (Define resolution of each bug, prioritize bugs and determine a schedule for all “To Be Fixed Bugs’)
There will be , slight Sluggish to load UI can be optimised to better load the application. there was bug while signing to login form is resolved now.
TEST COMPLETENESS (Define the criteria that will deem your testing complete)
Test completeness for the "Job Start" MERN application entails achieving 100% test coverage, executing all manual and automated test cases, and ensuring that all open bugs are either fixed or scheduled for resolution in the next release.
TEST DELIVERABLES
(Mention all the Test Artifacts that will be delivered during different phases of the testing lifecycle)
detailed screen shot of working applications. serveral functional tests are performed and tested. login bugs are optimised and error resolved using JWT.
RESOURCE AND ENVIRONMENT NEEDS
TESTING TOOLS
1. Windows/Linux/Mac OS 2. NPM NPX installed 3. active internet connection. 4. cloudnary cloud service with API keys and credientals. 5. mongodb Atlas
TEST ENVIRONMENT (Minimum hardware requirements that will be used to test the Application)
1. Windows/Linux/Mac OS 2. Chrome Browser 3. NPX / NPM 4. API Keys (Cloudnary ,Mongodb atlas)
ADDITIONAL COMMENTS
Everything and required details have been mentioned and submitted in the mentioned document.
TEST PLAN
ITEMS TO TEST | TEST DESCRIPTION | TEST START DATE | TEST END DATE | RESPONSIBLE PERSON | STATUS | COMMENTS
Test The Backend server | use postman to test the Mongodb test API calls | 2023-11-15 | 2023-11-17 | Austin | PASSED | done
Test the CRUD functionalities in commandline | use of commandline to test the actual application | 2023-11-19 | 2023-08-17 | Austin | PASSED | Done
Test Login and Register forms of application | Functionalities of the form applications | 2023-11-19 | 2023-11-22 | Austin | PASSED | Done
Integrate front end with backend | integrate all the front end side code with the backend to test and check the overall functionality | 2023-12-06 | 2024-01-11 | Austin | PASSED | Done
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To determine scope, you must – > Precise customer requirement > Project Budget > Product Specification > Skills & talent of your test team
Note on C24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The objective of the testing is finding as many software defects as possible; ensure that the software under test is bug free before release. To define the test objectives, you should do 2 following steps: > List all the software features (functionality, performance, GUI…) which may need to test. > Define the target or the goal of the test based on above features
Note on C40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A Testing Type is a standard test procedure that gives an expected test outcome. all Testing Types are aimed at achieving one common goal “Early detection of all the defects before releasing the product to the customer. There are tons of Testing Types for testing software product. Your team cannot have enough efforts to handle all kind of testing. As Test Manager, you must set priority of the Testing Types > Which Testing Types should be focused for web application testing? > Which Testing Types should be ignored for saving cost? The commonly used testing types are: 1. Unit Testing 2. API Testing 3. Integration Testing 4. System Testing 5. Install/Uninstall Testing 6. Agile Testing You need to decide based on your project scope, time and cost the testing type(s) required for your project
Note on C48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test Criteria is a standard or rule on which a test procedure or test judgment can be based. There’re 2 types of test criteria as following Suspension Criteria Specify the critical suspension criteria for a test. If the suspension criteria are met during testing, the active test cycle will be suspended until the criteria are resolved. Exit Criteria It specifies the criteria that denote a successful completion of a test phase. The exit criteria are the targeted results of the test and are necessary before proceeding to the next phase of development. Example: 95% of all critical test cases must pass.