## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT Schedule
Document created By: | Austin Doraiswamy
Document Created On: | 2023-10-22
Version: | 4
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## Project schedule complete
PROJECT PLAN IAC Internship Program 2023 - Full Stack Project Schedule
DOCUMENT VERSION: 4.0 | [6 empty] | INSTRUCTION TO USE THE PROJECT PLAN TEMPLATE: • All fields must be duly filled • The tasks/ activities listed in the template are bare minimum tasks and are not exhaustive. You will be required to add tasks/ activities based on the technology and the respective problem statement. • Clear all the sample data provided in the template. The data provided is only for reference purposes. • Mention the features you are working on the ”task name” field. • Mention the resource name who is responsible for completing a particular feature in the “assigned to” field. • Mention the start date and end date of a particular feature in the “start date” and “end date” field respectively. • Mention the time duration for completing a specific task in the “duration in days” field. • Select the current status of the feature you are working on from the drop-down list provided in the “status” field.
PROJECT NAME | JobStart
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | JobStart Fullstack MERN Job Portal
PROJECT SCOPE | To create a fully functional MERN job portal application with all the functionalities
PROJECT START DATE | 2023-10-22
PROJECT END DATE | 2024-01-28
OVERALL PROGRESS | Completed
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 | 1 Initiation
| 1.1 Identify business problem |  | 2023-10-22 | 2023-10-24 | 2 | COMPLETED
| 1.2 Recruit a team |  | 2023-10-23 | 2023-10-25 | 2 | COMPLETED
| 1.3 Create a project charter |  | 2023-10-24 | 2023-10-26 | 3 | COMPLETED
| 1.4 Requirement gathering |  | 2023-10-25 | 2023-10-27 | 1 | COMPLETED
2 | 2 Planning
| 2.1 Approval of business process |  | 2023-10-26 | 2023-10-30 | 4 | COMPLETED
| 2.2 Baseline project plan |  | 2023-10-26 | 2023-10-30 | 4 | COMPLETED
| 2.3 Team roles and responsibilities |  | 2023-10-26 | 2023-10-30 | 4 | COMPLETED
3 | 3 Execution
| 3.1 Finalize design |  | 2023-10-31 | 2023-10-31 | 1 | COMPLETED
| 3.2 Build |  | 2023-11-01 | 2024-01-28 | 88 | COMPLETED
3.2.1 Features
Registration page
Login page
Home page layout
| Navigation bar with logo |  | 2023-11-05 | 2023-11-10 | 5 | COMPLETED
| Job listing/ Job result page |  | 2023-11-11 | 2023-11-15 | 5
Job category & type information
Application page
| Apply for job/ Jobs page |  | 2023-11-16 | 2023-12-25 | 10 | COMPLETED
Employer information
Job details
Job description
Role
Required skills
| Footer |  | 2023-12-25 | 2023-12-28 | 3 | COMPLETED
Profile
| Dashboard |  | 2023-12-28 | 2024-12-01 | 4 | COMPLETED
Applied jobs/Posted jobs
Favorite jobs/candidates
Basic information of candidate/employer
| Post job |  | 13/01/2024 | 2024-12-26 |  | COMPLETED
Job title and desciption
Job category and type
Salary and qualification
Location
4 | Testing |  | 2024-01-26 | 2024-01-27 | 1 | COMPLETED
3.3.1 Manual testing
5 | Closure |  | 2024-01-28 | 2024-01-31 | 3 | COMPLETED